## Vendor 1
Category | Requirement | Performance |  |  |  | Grade
|  | Poor | Satisfactory | Ideal | Weight (1-5) | Poor = 1, Sat = 2, Ideal = 3 | Total
Project Type | We most highly value those projects that are "must-do" | Internal Only | Sustains existing capabilities and/or compliance | Performed to achieve compliance or the meet mandatory contract requirement | 5 | 0 | 0
Organizational Impact | We most highly value those projects that have influence of the most individuals within the organization (ours or client) | Affects less than 25% of both our and client population | Affects 25-75% of our and or client population members | Affects >75% of our and/or client population members | 3 | 0 | 0
Reach | We most highly value those projects that reach the broadest geographically | Local | Regional | Global | 3 | 0 | 0
Level of Sponsorship | We most highly value those projects that are supported by the influence of higher echelons in management | No charter or proof of sponsorship | Work is chartered, but below the C-Level of the organization | The work is chartered at the C-Level of the organization or its equivalent | 5 | 0 | 0
Public Impact | We most highly value those projects that reach the broadest spectrum of the public | Under 100,000 members of the public are impacted | 100,000 to 1,000,000 people will be directly impacted by the project | Over one million people will be directly impacted by the project | 2 | 0 | 0
Compliance | We most highly value those projects that facilitate regulatory or legal compliance | Has nothing to do with compliance | Supports compliance, albeit indirectly | Directly aimed at achieving or maintaining compliance | 5 | 0 | 0
Resources | We most highly value those projects that minimize resource (material and human) consumption | Consumes organizational resources for greater than one effort-year | Consumes organizational resources of less than an effort-year, but more than an effort-month | Consumes organizational resources of less than one effort-month | 4 | 0 | 0
Profit | We most highly value those projects that generate revenue | Loss | Neutral | Gain | 5 | 0 | 0
Market Potential | We most highly value those projects that engage us in growth markets | The market is declining or flat | The market is growing | This is a totally new market | 4 | 0 | 0
[7 empty] | Total: | 0