## Sheet1
Weekly Project Status Dashboard | [11 empty] | W= Win from last week P = Priorities for next week S = Where are you stuck? C = Describe reason for the R / Y /G stoplight color | Q4 2010 | [12 empty] | Q1 2011
[13 empty] | Week Beginning | [12 empty] | Week Beginning
Project / Customer | Type | Priority | PM | Consultant | Team Member 2 | Team Member 3 | Baseline Completion | Current Completion | Constraint | Estimated Cost | Actual Cost | Status Notes | 2010-10-04 | 2010-10-11 | 2010-10-18 | 2010-10-25 | 2010-11-01 | 2010-11-08 | 2010-11-15 | 2010-11-22 | 2010-11-29 | 2010-12-06 | 2010-12-13 | 2010-12-20 | 2010-12-27 | 2010-01-03 | 2010-01-10 | 2010-01-17 | 2010-01-24 | 2010-01-31 | 2010-02-07 | 2010-02-14 | 2010-02-21 | 2010-02-28 | 2010-03-07 | 2010-03-14 | 2010-03-21 | 2010-03-28
US-DOG System Improvements | Implementation | 3 | Mary | Moe | Larry | Curly & Shemp | 2011-03-01 | 2011-03-15 | Time | 515000 | 541680 | W=Completed site implementations for sites 10-12 P = Ramp up site 13 - 15 implementations, make travel arrangements for December team logistics, prepare for steering committee report S=Software vendor advised 2 week delay in media shipment for sites 45 & 15; need to define alternate options C=Software media shipment delay
Note on L4: teenaw: Currently projecting 5% ideficit to complete. Remediation recommendations forwarded to the client on 9/15. No response as yet.
Note on N4: teenaw: W=Resolved resource constraints P=Traiing at site 8; mobilize logistics for November travel S=Manager at site 8 out sick; don't know if she'll be back next week for training C=Need executive involvement to address contract interpretation issue
Note on O4: teenaw: W=Training at site 8; manager back online P=Document agenda for phase 3 scope meeting S=Not C=Schedule back on target
Note on P4: teenaw: W=Completed site implementations for sites 10-12 P = Ramp up site 13 - 15 implementations, make travel arrangements for December team logistics, prepare for steering committee report S=Software vendor advised 2 week delay in media shipment for sites 45 & 15; need to define alternate options C=Software media shipment delay